# Integrated Healthcare Management Platform

## HIV, Chronic Disease, Maternal Health & Appointment Management - 90-Day Action Plan

Prepared: January 06, 2026

# TABLE OF CONTENTS

1. Executive Summary

2. Market Validation

3. 30-60-90 Day Action Plan

4. Financial Projections

# 1. EXECUTIVE SUMMARY

## Business Overview

We are launching an AI-powered n8n automation solution specifically designed for healthcare facilities and hospitals managing HIV patient care programs. Our solution automates critical administrative workflows that currently consume 2+ hours per week (104-120 hours annually) of healthcare staff time.

## The Problem We Solve

Healthcare professionals managing HIV patients with comorbidities face a critical administrative burden: manually tracking multiple health conditions (HIV, diabetes, hypertension, TB), monitoring medication adherence across different therapies, managing maternal health for pregnant patients, tracking scattered clinic appointments, and generating weekly reports. This fragmented manual work consumes 15+ hours per week, diverts time from direct patient care, increases missed appointments, reduces medication adherence, and negatively impacts patient outcomes and engagement across all health conditions.

## Unique Value Proposition

Hyper-specialized for HIV patient management + comorbidity support (not generic automation)

AI-powered personalization for patient communications and health engagement

Integrated modules: Chronic disease management, maternal health tracking, medication adherence, appointment management

Saves 12-15 hours monthly per facility (vs 8-10 with HIV-only solution)

Improves patient adherence, reduces missed appointments, and improves clinical outcomes

40%+ gross margins with strong unit economics

Costs 70% less than competing EHR systems

Flexible n8n architecture with no vendor lock-in

## Integrated Platform Modules

Core HIV Management Module

Patient cohort tracking, ART adherence monitoring, missed appointment flagging, viral load tracking, treatment interruption alerts

Chronic Disease Management Module

Diabetes and hypertension patient tracking, medication monitoring, vital signs integration, comorbidity risk alerts, clinic visit scheduling

Maternal Health Tracking Module

PMTCT (Prevention of Mother-to-Child Transmission) monitoring, antenatal care scheduling, postnatal follow-up tracking, infant prophylaxis adherence, care coordinator alerts

Medication Adherence System

AI-powered medication reminders via WhatsApp, adherence pattern analysis, early warning for non-adherence, family/caregiver engagement, personalized intervention recommendations

Clinic Appointment Management

Automated appointment scheduling, multi-day reminder system, no-show prediction, appointment rescheduling workflow, clinic resource optimization

## Target Revenue Goal - First 90 Days

Primary Goal: 15-20 paying customers at UGX 2,956,300/month (Silver tier) = UGX 44,344,500 - UGX 59,126,000 monthly recurring revenue
Profitability Target: 16+ customers (break-even at UGX 18,500,000/month fixed costs)
Setup Fee Revenue: UGX 7,400,000-18,500,000 per customer (5-10 customers = UGX 37,000,000-185,000,000)
Module Upsell Potential: Additional UGX 370,000-740,000/month per facility for each integrated module (Maternal Health, Chronic Disease, etc.)

# 2. MARKET VALIDATION

## Evidence That Target Customers Exist

Target customers are clearly defined and actively seeking solutions:

Healthcare Subreddits: Posts documenting frustration with manual data entry and administrative burden

LinkedIn & Professional Forums: Consistent demand for healthcare automation and patient management solutions

Freelancer Platforms: Active job postings on Upwork/Fiverr for "healthcare automation" and "patient list management" at $120-$450/month budgets

Industry Networks: WhatsApp groups, HIVSA (HIV South Africa) networks, and healthcare IT forums show strong network effects

Geographic Validation: Initial research in Sub-Saharan Africa (Uganda, Zimbabwe, South Africa) shows critical need in resource-constrained healthcare systems

## Competitor Analysis

Current alternatives include:

Freelancer/Virtual Assistants: Cost: $120-$450/month | Problem: Inconsistent, unreliable, no continuity

Generic Automation (Zapier, IFTTT): Cost: $99-$300/month | Problem: Not specialized for healthcare, generic templates

EHR Systems (OpenMRS, DHIS2): Cost: $500-$5,000+/month | Problem: Expensive, complex, overkill for workflow automation

In-House Development: Cost: $3,000-$10,000+ upfront + ongoing | Problem: Requires technical staff, maintenance burden

## Our Competitive Advantage

Hyper-Specialization: Purpose-built for HIV care workflows + integrated comorbidity management (diabetes, hypertension, TB)

Comprehensive Health Coverage: Chronic disease monitoring, maternal health tracking, medication adherence, appointment management - all in one platform

Cost Leadership: 70% cheaper than EHR systems, more reliable than freelancers

AI Integration: OpenAI-powered personalization, patient engagement, and executive summarization

Flexibility: n8n-based architecture allows customization without vendor lock-in

Patient-Centric: Improves adherence rates, reduces missed appointments, and improves clinical outcomes

Proven Market Demand: Existing alternatives show clear willingness to pay ($120-$450/month) for similar single-purpose tools

## Potential Market Size (Target Region)

Geographic Focus: Western Uganda (Mbarara, Fort Portal, Kabale, Kisoro, Kanungu, Rukungiri, Ntungamo Districts)

Western Uganda has among the highest HIV prevalence rates in Uganda and Africa (12-18% in some districts, nearly 2x the national average). This concentrated high-burden region is our initial focus for rapid market penetration and relationship-building.

### Phase 1 - Western Uganda (Days 1-90)

Public Hospitals with HIV Programs: 3-4 facilities

District Health Offices/Programs: 2-3 programs

NGO Networks & Clinics: 2-3 networks

Private Clinics: 1-2 facilities

Academic/Teaching Institutions: 1 facility

Phase 1 Target: 10-15 customers (conservative 50% conversion from 20 prospects)

### Phase 2 - Western Uganda Expansion (Months 4-6)

Secondary District Facilities: 12-15 additional facilities

Referral Network Growth: 10-15 additional prospects from existing customer referrals

Phase 2 Target: 25-35 total customers in Western Uganda by Month 6

### Long-term (Pan-Uganda Expansion)

Central Uganda (Kampala Metro): 40-60 facilities

Other Regions (after Western Uganda proof): 100-150+ facilities

Total Pan-Uganda TAM: 150-250+ HIV care facilities

Phase 1 Revenue Potential (Western Uganda, 90 days): 10-15 customers × UGX 2,956,300/month (avg Silver tier) = UGX 29,563,000-44,344,500 MRR by Day 90

Phase 2 Revenue Potential (Extended Western Uganda, 6 months): 25-35 customers × UGX 2,956,300/month = UGX 73,907,500-103,470,500 MRR by Month 6

Long-term Pan-Uganda TAM (12+ months): 150-250 facilities × UGX 2,956,300/month = UGX 443,445,000-739,075,000 MRR potential

# 3. 30-60-90 DAY ACTION PLAN

## Days 1-30: Foundation & Initial Outreach

### Deliverables

Complete and test n8n workflow with real healthcare data (HIV + comorbidity management)

Develop 14-day free trial setup process

Create professional website with demo video

Design branded presentation deck and case study template

Identify and validate first 10 target customers (see Client Outreach Plan)

Prepare personalized outreach messages for LinkedIn

Build integrated modules: Chronic Disease Management, Maternal Health, Medication Adherence, Appointment Management

### Weekly Breakdown

Week 1-2: Technical Setup

Finalize n8n workflow with real-world sample data from HIV care facilities

Build integrated modules: Chronic Disease tracking, Maternal Health monitoring, Medication Adherence system, Appointment Management

Set up Google Sheets templates for all modules (HIV, CD, Maternal, Medications, Appointments)

Configure OpenAI API and WhatsApp Business API integrations for patient engagement

Complete n8n to Google Drive integration for automated report delivery across all modules

Week 2-3: Marketing & Content

Design professional 1-page website highlighting key benefits

Create 2-3 LinkedIn thought leadership posts on healthcare automation

Record 3-5 minute demo video showing workflow in action

Develop pricing page and comparison chart vs. competitors

Week 3-4: Prospect Research & Initial Outreach

Research and identify 10 potential first customers (healthcare administrators/directors)

Establish LinkedIn connections with decision-makers (Days 28-30)

Prepare personalized outreach messages with clear value prop

Schedule 5-8 discovery calls for Week 5

### Expected Outcome - Days 1-30

✓ 3-5 pilot customers in early talks (scheduled for demos Day 31+)

✓ 50+ LinkedIn connections with qualified decision-makers

✓ Fully functional workflow and trial setup

✓ Website and marketing collateral live

## Days 31-60: Refinement, Early Growth, & First Pilots

### Deliverables

Conduct 5-8 discovery calls and personalized demos (HIV + comorbidity management)

Gather feedback from pilot customers on all integrated modules (HIV, Chronic Disease, Maternal Health, Medication Adherence, Appointment Management)

Secure 3-5 pilot customers with full platform access (discounted or free trial)

Acquire 5-8 new qualified leads through content and outreach (emphasize integrated platform)

Launch LinkedIn advertising campaign targeting healthcare administrators with emphasis on time-savings and clinical outcomes

Develop first customer testimonial and case study showcasing module integration benefits

Create detailed implementation guide for all integrated modules

### Weekly Breakdown

Week 5-6: Demo & Pilot Conversion

Conduct 5-8 discovery calls to understand pain points and customize pitch

Deliver personalized 30-minute demos with pilot data

Secure commitment from 3-5 pilot customers (free/discounted trial)

Send trial setup instructions and provide onboarding support

Week 7-8: Iteration & New Outreach

Collect feedback from pilot customers (Week 5-6 trials now running)

Iterate and optimize n8n workflows based on real feedback

Launch 30-targeted LinkedIn ads with case study snippets

Identify next 5-8 qualified leads from warm network and content engagement

Schedule discovery calls with new prospects (Week 9+)

### Expected Outcome - Days 31-60

✓ 3-5 active pilot customers providing real-world feedback

✓ 1-2 customers ready to convert to paid subscriptions (Silver tier)

✓ 5-8 new qualified leads in demo pipeline

✓ First customer testimonial and mini case study published

✓ Optimized workflows based on pilot feedback

## Days 61-90: Scale & First Revenue Acceleration

### Deliverables

Convert 5-10 pilot and lead customers to paid subscriptions with integrated platform

Achieve 15-20 total paying customers (break-even + growth)

Publish first comprehensive customer case study with results across multiple modules

Launch district-level and multi-facility outreach with module-specific value propositions

Develop customer success playbook for onboarding all integrated modules

Plan expansion to secondary products (advanced clinical analytics, patient portal) or regions

Activate module upsells: Maternal Health, Chronic Disease Management, and Enhanced Appointment Management for existing customers

### Weekly Breakdown

Week 9-10: Conversion & Case Study

Convert 3-5 active pilots to paid Silver tier customers

Follow up with 5-8 demo pipeline prospects for decision

Document 2-3 customer case studies with quantified results (e.g., "Saved 8 hours/week")

Publish case study across website, LinkedIn, and email

Week 11-12: Expansion & Optimization

Target district programs and multi-facility organizations

Convert remaining demo leads (2-5 additional customers)

Develop customer success documentation and self-serve onboarding guide

Analyze MoM growth rate and plan next 90-day expansion

### Expected Outcome - Days 61-90

✓ 15-20 paying customers at UGX 2,956,300/month Silver tier

✓ Monthly Recurring Revenue (MRR): UGX 44,344,500-UGX 59,126,000

✓ Profitability achieved (break-even at 16 customers)

✓ 2-3 published case studies demonstrating customer success

✓ Clear growth momentum and expansion roadmap

✓ 30-50+ leads in pipeline for next 90 days

# 4. FINANCIAL PROJECTIONS

## Pricing Structure

| Tier | Monthly Price | Target Customer | Annual Value |
| --- | --- | --- | --- |
| Bronze | UGX 1,476,300 | Small clinics, NGOs | UGX 17,715,600 |
| Silver | UGX 2,956,300 | Hospitals, district programs | UGX 35,475,600 |
| Gold | UGX 5,546,300 | Multi-facility, regional programs | UGX 66,555,600 |

One-Time Setup Fee: UGX 7,400,000 per customer (covers initial workflow customization, data migration, training)

## Cost Breakdown - Silver Tier (UGX 2,956,300/month)

| Cost Category | Monthly Cost |
| --- | --- |
| n8n Cloud Workspace (advanced) | UGX 185,000 |
| OpenAI API usage (1000+ messages/month) | UGX 92,500 |
| Google Workspace/Sheets (shared) | UGX 37,000 |
| WhatsApp Business API (per customer) | UGX 148,000 |
| Support & Onboarding (30 min/month) | UGX 555,000 |
| COGS Total | UGX 1,017,500 |

Gross Margin Calculation:
Revenue: UGX 2,956,300/month
COGS: UGX 1,017,500/month
Gross Profit: UGX 1,938,800/month per customer
Gross Margin: 65.6%

## Break-Even Analysis

Fixed Costs (estimated monthly): UGX 18,500,000
  - Founder salary/living expenses: UGX 11,100,000
  - Marketing & content: UGX 4,440,000
  - Tools/infrastructure: UGX 2,960,000

Break-Even Point: 
UGX 18,500,000 ÷ UGX 1,938,800 contribution per Silver customer = 9.5 customers

Conservative Estimate: 12-16 Silver tier customers = profitability

Timeline: Achievable by Day 80-90 with 3-5 pilot conversions + 5-10 new sales

## Revenue Projection - First 6 Months

| Month | Customers | MRR (Avg UGX 2,956,300) | Setup Fee Revenue |
| --- | --- | --- | --- |
| Month 1 (Days 1-30) | 0 | UGX 0 | UGX 0 |
| Month 2 (Days 31-60) | 3-5 | UGX 8,868,900-14,781,500 | UGX 22,200,000-37,000,000 |
| Month 3 (Days 61-90) | 12-18 | UGX 35,475,600-53,213,400 | UGX 14,800,000-29,600,000 |
| Month 4 | 18-25 | UGX 53,213,400-73,907,500 | UGX 14,800,000-29,600,000 |
| Month 5 | 25-35 | UGX 73,907,500-103,470,500 | UGX 14,800,000-29,600,000 |
| Month 6 | 35-45 | UGX 103,470,500-133,033,500 | UGX 7,400,000-22,200,000 |

Total Revenue Projection (6 months): UGX 462,500,000 - UGX 740,000,000 (including setup fees)
By Month 6 MRR: UGX 103,470,500 - UGX 133,033,500 (35-45 customers)